## Sheet1
MOHCD - Retention Release Requirements
2017-07-28 |  | *These requirements apply regardless of the source of funds for the Retention payment(s)
Required | Received/OK
Contractor provides Owner with AIA G702 / G703 Pay Application including request for Retention Release.
General Contractor - All proper Lien Releases received.
Conditional Waiver and Release upon Final Payment - With Pay Application
Unconditional Waiver and Release upon Final Payment - upon Payment (prior to Conversion)
Subcontractor Waivers
No Liens or Stop Notices have been filed against the Project and no claims are pending.
Certification by Engineer, (where applicable) that the work was completed as per City approved plans and specifications.
Certificate of Substantial Completion executed by Architect, Contractor and Owner acknowledging that all work is in
substantial conformance with Contract Documents.
Recorded Notice of Completion (filed by Owner within 10 days of completion) - Recorded and 30 days passed
Received: Date of Recordation _________________________
30 Day Period Ends:___________________
Final Certificate of Occupancy (only New construction and Vacated Rehab)
Department of Building Inspection and Other Agencies that all permitted Workis complete and in conformance with
Codes and Regulations - Evidenced by FINAL Permit Cards issued to Owner (and MOHCD in electronic format)
Preliminary Title Received, if required, Showing No Recorded Liens.
Evidence of Continued Insurance Coverage (Ins. Certificates)
Project Directory - Listing all Principals, Design firms, Subcontractors and Suppliers with Phone and/or Email contact
The Project remaining hard cost contingency is in balance and adequate to complete the Project (for Early release
of retention prior to completion)
Issuance to Owner of all Completion Documents and Owner's acknowledgement of receipt in writing of:
As-Built Plans in Hard Copy and Electronic Format (MOHCD shall receive Electronic format)
As-Built ALTA Survey (New construction only, and may be provided prior to conversion)
Guarantees and Warranties for all Equipment, Materials and Work - Including GC Call-Back Process & Contact info
Keys, Keyfobs, Instruction Manuals, Software, Training Videos and Training completed
Inspection Reports (Course of Construction, and Final) Including but not limited to:
Equipment and Systems Test Reports (Backflow prevention, Elevator State Inspection, Fire Supression and Alarm, etc.)
Materials Testing Reports
Crack and Settlement Survey (including Report comparing initial projected settlement v. actual at Completion)
Extra (stock) Materials have been delivered to Site and properly stored
All "Punch List" items have been completed, inspected and accepted by Architect and Owner - In Writing *
|  | * | Punch List items that remain incomplete at the time of Request to Release Retention shall have up to 150% of
their value withheld from the Request for Retention value until complete and accepted and this value documented
with AIA G706 (Contractors Affidavit of Payment of Debits or Claims) or other mutually acceptable form.